## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1 | Collect and generate structured enterprise data |  | – |  | Completed
1 | 2 | 2 | Refine data model and regenerate datasets |  | 1 |  | Completed
2 | 2 | 3 | Generate semi-structured and unstructured documents |  | 1 |  | Completed
2 | 3 | 4 | Introduce metadata and contradictions |  | 3 |  | Completed
3 | 3 | 5 | Ingest data into Neo4j knowledge graph |  | 4 |  | Completed
3 | 4 | 6 | Refine graph schema and enforce sparsity |  | 5 |  | Completed
4 | 4 | 7 | Implement entity extraction and resolution |  | 5 |  | Completed
4 | 5 | 8 | Improve entity resolution and external entity handling |  | 7 |  | Completed
5 | 5 | 9 | Build embeddings and FAISS indexes |  | 8 |  | Completed
5 | 6 | 10 | Implement hybrid RAG pipeline |  | 9 |  | Completed
6 | 6 | 11 | Validate RAG and build interactive UI |  | 10 |  | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Initial structured data generation (CSV) | 2008-12-01 | 2014-12-01 |  | Coding | Completed
2 | 2 | Data regeneration & schema fixes | 2015-12-01 | 2021-12-01 |  | Coding | Completed
2 | 2 | Email & report document generation | 2015-12-01 | 2021-12-01 |  | Coding | Completed
3 | 3 | Metadata creation & contradiction tagging | 2022-12-01 | 2028-12-01 |  | Coding | Completed
3 | 3 | Neo4j ingestion & indexes | 2022-12-01 | 2028-12-01 |  | Coding | Completed
4 | 4 | Entity extraction using NLP | 2029-12-01 | 2005-01-01 |  | Coding | Completed
4 | 4 | Resolution threshold tuning | 2029-12-01 | 2005-01-01 |  | Design | Completed
5 | 5 | Embeddings & FAISS indexing | 2006-01-01 | 2020-01-01 |  | Coding | Completed
5 | 5 | Hybrid retrieval logic | 2006-01-01 | 2020-01-01 |  | Coding | Completed
6 | 6 | Validation, golden queries & UI | 2021-01-01 | 1930-01-01 |  | Integration | Completed
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-12-10 | Initial data lacked realism | Regenerated datasets with hierarchy
2 | 2025-12-18 | Schema changes broke earlier data | Iterative regeneration & fixes
3 | 2025-12-26 | Graph becoming too dense | Enforced sparsity rules
4 | 2026-01-03 | Entity ambiguity across docs | Added confidence thresholds
5 | 2026-01-14 | Risk of hallucinated answers | Added strict source validation
6 | 2026-01-26 | Validation failures in edge cases | Introduced golden queries

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7